**ORATIA RATEPAYERS & RESIDENTS**

**PROJECT STATUS LIST - HALLS + DOMAIN**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **TITLE** | **BRIEF** | **LOCATION** | **STATUS** | **Date started** | **Date Complete** | **P.M.** |
| 6 x Tables | Repair or Replace 6 square tables | Small Hall | 3 done awaiting Roko to put tops on 3 more. | September 2012 |  | P.S. |
| Trestle Tables | Replace new trestle tables, apply for funding. | Small Hall | Costs with Paulette  ???? Debbie (13/2) | August 2012 |  | D.H. P.T. |
| Bathroom Signs | Clear signage required for New Disabled toilets, to make it clear it is available for women and parents, as well as men. | Settlers Hall | Gary to Cost | October 2012 |  | G.H. |
| Curtains | New Curtains over sliding doors. Must create blackout for Film Night. Must be fire retardant and comply with safety standards. Now urgent. | Settlers Hall | Measuring.  12/3/ Dave will contact Jo and Paulette to see where project is at. Curtains required by April for film nights. | August  2012 |  | P.T.  J.H.  D. |
| Heating | Effective Heating (radiant) for the Halls. Must work with coin system. | Settlers + Small | - Missed out on trusts funding.  Costs  Settlers Hall = Electrician $3136 +Devi Heating $5238.25 = Totl $8374.25  Church Hall = Electrician $2147 + Heaters $ 3453 = $5590  Information on the enersave product + why radiant heat here:  <http://www.enersave.co.nz/products/ceiling___wall_heating/ceiling_heating/energostrip> | July-ish  2012 |  | P.S. |
| Oratia Apple | Next issue. |  | Call for submissions - Autumn Addition. | October  2012 |  | J.B. + R. K |
| Update Hire Contract | Update the hireage contract and rules, and replace the framed copy in the halls | Settlers + Small | Contract and rules updated. Still need to put them in the frame | Aug  2012 |  | P.S. |
| Domain Design | Get awesome design for Domain Area | Domain | 1. Get in touch with Claire Louisse to get firm timings on project |  |  | P.S. |

**PROJECT STATUS LIST - OTHER COUNCIL STUFF**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **TITLE** | **BRIEF** | **LOCATION** | **STATUS** | **Date started** | **Date Complete** | **P.M.** |
| UNITARY PLAN | Make submission on Unitary Plan - Gather community info. Create form. Penny and Gary | Small Hall | 3 done awaiting Roko to put tops on 3 more. | September 2012 |  | P.S. + G.H. |
| **AGM** | AGM is set  - Date set of Tuesday May 28th  - Ensure end of year financials are prepared.  - Gary to book a speaker  - discussed changing memberhip fees and area as per Oratia LAP boundarys.  - Book main Hall | Settlers Hall |  | **May 28th 2013** |  |  |

**DOMAIN Project Ideas Requested by Members Not yet in progress**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PROJECT TITLE** | **BRIEF** | **LOCATION** | **STATUS** | **Date started** | **Date Completed** | **P.M.** |
| Verandah + Gates | Put a verandah on Settlers Hall deck to provide outside space  Possible maintenance on deck (boards soft) and paint railings. | Settlers Hall | Consider options and effect on sun.  Awaiting maintenance review from council (13/3) |  |  | D.H. |
| Signage | Re sign the Oratia Settlers Hall and Sign for the Small Hall. | Settlers Hall | Penny to mock up in photoshop. |  |  | P.S. |
| Ashtrays on deck | Penny has put forward some examples to Debbie | Settlers Hall |  |  |  |  |
| Outside Lighting | ? |  |  |  |  |  |
| Wifi | ? |  |  |  |  |  |
| New Joinery to replace brown sliding doors. | ? |  |  |  |  |  |

**Completed Projects**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PROJECT TITLE** | **BRIEF** | **LOCATION** | **STATUS** | **Date started** | **Date Completed** | **P.M.** |
| Website | Create a website for the Ratepayers | Cyberspace | Complete |  | July | P.S. |
|  |  |  |  |  |  |  |

**ON HOLD OR CANCELLED**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tree Removal | Remove Trees along east of Small Hall. No longer required. | Domain | Some trees were trimmed. Now Awaiting domain plan for changes | | | October  2012 | |  | | P.S. |
| Gardens | Improve Gardens around halls. Gardens require work and boxing and wood edging needs .replacing | Outside halls | | Awaiting Plans for domain |  | |  | | P.S. | |